## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Develop Hardware Requirements | 5 | 150 |  |  |  | 150
| Develop Software Requirements | 5 | 150 |  |  |  | 150
| Research Software Vendors | 10 | 370 |  |  |  | 370
| Research Hardware Vendors | 10 | 360 |  |  |  | 360
| Develop Preliminary Network Design | 16 | 576 |  |  |  | 576
| Determine Computer Placement | 5 | 335 |  |  |  | 335
| Develop Implementation Schedule | 40 | 2200 |  |  |  | 2200
| Develop Computer Test Plan | 8 | 968 |  |  |  | 968
| Develop Network Test Plan | 24 | 1752 |  |  |  | 1752
| Subtotal | 123 | 6861 | 0 | 0 | 0 | 6861
PROJECT DEVELOPMENT | Install Computers | 28 | 700 | 250000 |  |  | 250700
| Procure Software | 10 | 370 | 8200 |  |  | 8570
| Procure Hardware | 10 | 360 |  |  |  | 360
| Install Software | 20 | 740 | 5000 |  |  | 5740
| Install Cabling / Patch Cables | 80 | 2880 | 10525 |  |  | 13405
| Install Security Measures | 20 | 1960 | 8200 |  |  | 10160
| Install Access Points/Routers/Modems | 12 | 432 | 3426 |  |  | 3858
| Install Servers | 4 | 144 | 1800 |  |  | 1944
| Install Switches / RJ45 Jacks | 4 | 144 | 51397 |  |  | 51541
| Perform Device Unit/Integration Tests | 12 | 348 |  |  |  | 348
| Perform Network Unit/Integration Tests | 80 | 2320 |  |  |  | 2320
| Subtotal | 280 | 10398 | 338548 | 0 | 0 | 348946
PROJECT DELIVERY | Connect to Network | 8 | 288 |  |  |  | 296
| Configure Network | 20 | 720 |  |  |  | 740
| Ensure Network Functionality | 40 | 2600 |  |  |  | 2640
| Test Network Speeds | 20 | 769 |  |  |  | 789
| Test Network Coverage | 20 | 1300 |  |  |  | 1320
| Perform Penetration Testing | 24 | 696 |  |  |  | 720
| Subtotal | 132 | 6373 | 0 | 0 | 0 | 6505
PROJECT MANAGEMENT | Stakeholder Meetings | 16 | 536 |  |  |  | 552
| Team Meetings | 32 | 2240 |  |  |  | 2272
| Third-Party Vendor Interface | 12 | 480 |  |  |  | 492
| Schedule Control | 24 | 720 |  |  |  | 744
| Document Meetings & Produce Reports | 12 | 840 |  |  |  | 852
| Quality Assurance | 80 | 3200 |  |  |  | 3280
| Overall Project Management | 200 | 8000 |  |  |  | 8200
| Subtotal | 376 | 16016 | 0 | 0 | 0 | 16392
|  | LABOR HOURS | HOURLY WAGE ($) |  |  |  | TOTAL SALARY
SALARIES COST | Project Manager | 376 | 40 |  |  |  | 15040
| Agenda Director | 171 | 30 |  |  |  | 5130
| Systems Administrator | 58 | 25 |  |  |  | 1450
| Network Engineer | 260 | 36 |  |  |  | 9360
| Software Engineer | 73 | 37 |  |  |  | 2701
| Testing Engineer | 228 | 29 |  |  |  | 6612
| Subtotal | 1166 | 197 |  |  |  | 1363
Subtotals |  | 911 | 39845 | 338548 | 0 | 0 | 393744
Risk (Contingency) |  | 40 | 3040 | 5000 | 0 | 500 | 8540
Total (Scheduled) |  | 951 | 42885 | 343548 | 0 | 500 | 402284

## Expenditures Over Time
Expenditures Over Time
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install Network Hardware | 59225 | 2018-11-07 | Ethernet cables are required for connecting devices to the network. Servers are needed to provide higher failover and faster access. Access points are needed to provide sufficient coverage.
|  | Install Software & Security | 8200 | 2018-11-09 | Servers are needed to provide higher failover and faster access.
|  | Configure Network | 1080 | 2018-12-10 | The network needs to be configured to allow devices to connect to the intranet.
|  | Perform Acceptance Test | 580 | 2018-01-01 | Labor for testing engineer to ensure network functionality meets company needs.
|  | Perform Post Project Review | 480 | 2018-01-01 | Labor for project manager to document lessons learned for future projects.
|  | Provide Warranty Support | 270 | 2018-11-07 | Servers will need extended warranties which are 15% of product price.
|  | Achieve Materials | 9131 | 2018-11-09 | Delivery fees for 2 day shipping averages roughly 10%.
|  | Subtotal | 78966
| PLANNING (RFP) | Research | 365 | 1900-01-19 | Labor was required to thoroughly research vendors prior to committing to contracts.
|  | Train Team Members | 1000 | 2018-11-06 | Team members required coaching to ensure quality due to lower inexperience.
|  | Develop Schedule | 2800 | 2018-11-05 | Labor was required for the project manager and agenda director to develop a schedule to meet deadline requirements.
|  | Develop Device Testing Plans | 968 | 2018-11-20 | Labor for the agenda director, systems administrator, & software engineer to design test plans for computers, connected hardware, and software implemenation.
|  | Develop Network Testing Plans | 736 | 2018-12-05 | Labor for the agenda director, systems administrator, & software engineer to design test plans for computers, connected hardware, and software implemenation.
|  | Develop Network Design | 576 | 2018-12-07 | Labor is required to organization where cabling and access points will be installed.
|  | Subtotal | 6445
| CONSTRUCTION | Install CAT7 Cabling | 10400 | 2018-11-12 | Cabling needs to be installed throughout the 16,000 square feet of the facility.
|  | Install Patch Cabling | 125 | 2018-11-07 | Patch cabling is required to connect cables and devices.
|  | Install RJ45 Jacks | 350 | 2018-11-07 | RJ45 jacks are needed to provide connectivity with the devices on the network.
|  | Perform Acceptance Test | 1300 | 2018-11-19 | RJ45 jacks and patch cables need to be tested for quality and connectivity.
|  | Perform Post Project Review | 290 | 2018-12-26 | Review is needed to determine if and when additional RJ45 jacks or patch cabling is required.
|  | Subtotal | 12465
| TEST & DELIVERY | Test Connection Speeds | 720 | 2018-12-27 | Labor is required for the network to be checked for speeds.
|  | Test Connection Zones | 720 | 2018-12-27 | Labor is required for the network to be checked for where devices can connect to the network.
|  | Test Devices | 348 | 2018-11-14 | The devices need to be tested to ensure speed and software access is adequate.
|  | Test Security | 696 | 2018-12-20 | The network and devices need to be tested to ensure protection against data theft or manipulation.
|  | Provide Warranty Support | 4880 | 2018-01-07 | Up to 80 hours of labor needs to be set aside for possible hardware or software training and/or re-configuration.
|  | Subtotal | 2484
| PROJECT TOTAL |  | 100360

## Cumulative Project Costs
Projected vs. Actual Costs
WEEKLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| WEEK | PROJECTED WEEKLY COST | ACTUAL WEEKLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 262505 | 265165 | 262505 | 265165
| 2 | 1550 | 3875 | 264055 | 269040
| 3 | 1645 | 3901 | 265700 | 272941
| 4 | 17827 | 21467 | 283527 | 294408
| 5 | 53639 | 55103 | 337166 | 331945
| 6 | 720 | 2400 | 337886 | 351911
| 7 | 2600 | 4280 | 340486 | 356191
| 8 | 2600 | 4712 | 343086 | 360903
| 9 | 1620 | 3300 | 344706 | 364203