## WBS
WBS Number | Task Name | WBS Description | Must Start by Date | Must End by Date | Task Level of Effort (in hours) | Task Duration (in days) | Predecessor (Finish-to-Start Dependency) (comma separated) | Planned Start Date | Actual Start Date | Status | Reason Description | Date of Completion | Resource Name(s) | Author (of item for follow-up questions)
1 | Install Computers | All 500 computers will need to be installed in their respective places. | 2018-11-07 | 2018-11-15 | 40 | 5 |  | 2018-11-07 | 2018-11-07 | Complete |  | 2018-11-15 | Betsy Knowit | Felicia Ainslie
1.1 | Install all desktop monitors | Place desktop monitors in their respective places along with the appropriate cabling. | 2018-11-07 | 2018-11-09 | 8 | 1 |  | 2018-11-07 | 2018-11-07 | Complete |  | 2018-11-11 | Betsy Knowit | Felicia Ainslie
1.2 | Install all desktop towers | Place desktop towers in their respective places along with the appropriate cabling & power strips. | 2018-11-07 | 2018-11-09 | 8 | 1 | 1.1 | 2018-11-07 | 2018-11-07 | Complete |  | 2018-11-11 | Betsy Knowit | Felicia Ainslie
1.2.1 | Connect devices to power supply | Plug monitors and towers into power strips. Plug power strips into the wall. Use clips if necessary to gather cords. | 2018-11-07 | 2018-11-09 | 2 | 1 | 1.1, 1.2 | 2018-11-07 | 2018-11-07 | Complete | Delayed due to insuffiecient power strips. | 2018-11-12 | Betsy Knowit | Felicia Ainslie
1.2.2 | Connect devices to eachother | Plug monitors into towers.Use clips if necessary to gather cords. | 2018-11-07 | 2018-11-09 | 2 | 1 | 1.1, 1.2 | 2018-11-07 | 2018-11-07 | Complete |  | 2018-11-11 | Betsy Knowit | Felicia Ainslie
1.2.3 | Test devices | Ensure that devices power on correctly. | 2018-11-12 | 2018-11-12 | 4 | 1 | 1.2.1, 1.2.2 | 2018-11-12 | 2018-11-11 | Complete | Delayed due to insuffiecient power strips. | 2018-11-12 | John Doughe | Felicia Ainslie
1.2.4 | Test login credentials | Ensure that login credentials for the respective devices work. | 2018-11-12 | 2018-11-12 | 4 | 1 | 1.2.1, 1.2.2 | 2018-11-12 | 2018-11-13 | Complete | Delayed due to insuffiecient power strips. | 2018-11-13 | John Doughe | Felicia Ainslie
1.3 | Install all laptops | Place desktop monitors in their respective places along with the appropriate cabling & power strips. | 2018-11-13 | 2018-11-14 | 4 | 1 |  | 2018-11-12 | 2018-11-13 | Complete |  | 2018-11-13 | Betsy Knowit | Felicia Ainslie
1.3.1 | Connect devices to power supply | Plug laptops into power strips. Plug power strips into the wall. Use clips if necessary to gather cords. | 2018-11-13 | 2018-11-14 | 4 | 1 | 1.3 | 2018-11-12 | 2018-11-13 | Complete | Delayed due to insuffiecient power strips. | 2018-11-13 | Betsy Knowit | Felicia Ainslie
1.3.2 | Test devices | Ensure that devices power on correctly. | 2018-11-14 | 2018-11-15 | 2 |  | 1.3.1 | 2018-11-14 | 2018-11-13 | Complete | Delayed due to insuffiecient power strips. | 2018-11-14 | John Doughe | Felicia Ainslie
1.3.3 | Test login credentials | Ensure that login credentials for the respective devices work. | 2018-11-14 | 2018-11-15 | 2 |  | 1.3.1 | 2018-11-14 | 2018-11-14 | Complete |  | 2018-11-15 | John Doughe | Felicia Ainslie
2 | Install Software | Software relating to company needs will need to be installed. This will include but not be limited to the customer relations management system and security program(s). | 2018-11-16 | 2018-11-30 | 40 | 7 | 1 | 2018-11-16 | 2018-11-16 | Complete |  | 2018-11-29 | Betsy Knowit | Felicia Ainslie
2.1 | Research software options | Complete thorough research regarding software options and pricing. | 2018-11-16 | 2018-11-22 | 10 | 2 |  | 2018-11-16 | 2018-11-16 | Complete |  | 2018-11-16 | Betsy Knowit | Felicia Ainslie
2.2 | Purchase Software | Sign contracts and purchase software for all Future Tech Inc. devices. | 2018-11-16 | 2018-11-20 | 10 | 2 | 2.1 | 2018-11-16 | 2018-11-16 | Complete |  | 2018-11-16 | Betsy Knowit & Felicia Ainslie | Felicia Ainslie
2.2.1 | Sign Contract for Salesforce CRM | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-20 | 2 |  | 2.1 | 2018-11-16 | 2018-11-16 | Complete | Complications in contract negotiation delayed completion. | 2018-11-26 | Felicia Ainslie | Felicia Ainslie
2.2.2 | Sign Contract for Microsoft Office 365 | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-21 | 2 |  | 2.1 | 2018-11-16 | 2018-11-17 | Complete | Vendor rescheduled. | 2018-11-17 | Felicia Ainslie | Felicia Ainslie
2.2.3 | Sign Contract for Paycom | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-21 | 2 |  | 2.1 | 2018-11-16 | 2018-11-16 | Complete |  | 2018-11-16 | Felicia Ainslie | Felicia Ainslie
2.2.4 | Sign Contract for Pidgin | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-21 | 1 |  | 2.1 | 2018-11-16 | 2018-11-19 | Complete | Vendor rescheduled. | 2018-11-19 | Felicia Ainslie | Felicia Ainslie
2.2.5 | Sign Contract for TeamViewer | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-22 | 1 |  | 2.1 | 2018-11-16 | 2018-11-16 | Complete |  | 2018-11-16 | Felicia Ainslie | Felicia Ainslie
2.2.6 | Sign Contract for Basecamp | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-16 | 2018-11-22 | 1 |  | 2.1 | 2018-11-16 | 2018-11-18 | Complete | Vendor rescheduled. | 2018-11-19 | Felicia Ainslie | Felicia Ainslie
2.2.7 | Sign Contract for Avast | Provide payment to vendor and develop an agreement on terms & conditions. | 2018-11-17 | 2018-11-22 | 1 |  | 2.1 | 2018-11-17 | 2018-11-19 | Complete | Vendor rescheduled. | 2018-11-19 | Felicia Ainslie | Felicia Ainslie
2.3 | Install Software | Software needs to be installed on all computers. | 2018-11-20 | 2018-11-23 | 20 | 3 | 2.2 | 2018-11-20 | 2018-11-17 | Complete |  | 2018-11-28 | Betsy Knowit | Felicia Ainslie
2.3.1 | Install Salesforce CRM | Install Salesforce CRM on all devices & create user login credentials. | 2018-11-22 | 2018-11-26 | 6 | 1 | 2.2 | 2018-11-22 | 2018-11-27 | Complete | Delayed to do contraction negotiaion issues. | 2018-11-28 | Betsy Knowit | Felicia Ainslie
2.3.2 | Install Microsoft Office 365 | Install Microsoft Office 365 on all devices & create user login credentials. | 2018-11-22 | 2018-11-28 | 6 | 1 | 2.2 | 2018-11-22 | 2018-11-19 | Complete |  | 2018-11-20 | Betsy Knowit | Felicia Ainslie
2.3.3 | Install Paycom | Install Paycom on all devices & create user login credentials. | 2018-11-23 | 2018-11-26 | 3 | 1 | 2.2 | 2018-11-23 | 2018-11-19 | Complete |  | 2018-11-19 | Betsy Knowit | Felicia Ainslie
2.3.4 | Install Pidgin | Install Pidgin on all devices & create chat rooms for all departments. | 2018-11-23 | 2018-11-26 | 3 | 1 | 2.2 | 2018-11-23 | 2018-11-20 | Complete |  | 2018-11-20 | Betsy Knowit | Felicia Ainslie
2.3.5 | Install TeamViewer | Install TeamViewer on all devices. | 2018-11-23 | 2018-11-26 | 3 | 1 | 2.2 | 2018-11-23 | 2018-11-19 | Complete |  | 2018-11-19 | Betsy Knowit | Felicia Ainslie
2.3.6 | Install Basecamp | Install Basecamp on all devices assigned to technical or project involved staff members & create team groups & user login credentials. | 2018-11-26 | 2018-11-28 | 6 | 1 | 2.2 | 2018-11-26 | 2018-11-20 | Complete |  | 2018-11-27 | Betsy Knowit | Felicia Ainslie
2.3.7 | Install Avast | Install Avast on all devices. | 2018-11-26 | 2018-11-28 | 6 | 1 | 2.2 | 2018-11-26 | 2018-11-21 | Complete |  | 2018-11-23 | John Doughe | Felicia Ainslie
2.4 | Test Software & Logins | Test each user's login credentials and ensure products work accordingly. | 2018-11-28 | 2018-11-30 | 10 | 2 | 2.2, 2.3 | 2018-11-28 | 2018-11-26 | Complete |  | 2018-11-29 | John Doughe | Felicia Ainslie
2.4.1 | Test Logins | Test that user logins work correctly with temp passwords and force password changes. | 2018-11-28 | 2018-11-29 | 6 | 1 | 2.2, 2.3 | 2018-11-28 | 2018-11-26 | Complete |  | 2018-11-29 | John Doughe | Felicia Ainslie
2.4.2 | Test Access | Test that users can only access their set groups / chats. | 2018-11-28 | 2018-11-29 | 4 | 1 | 2.2, 2.3 | 2018-11-28 | 2018-11-26 | Complete |  | 2018-11-29 | John Doughe | Felicia Ainslie
3 | Install Network Hardware | The hardware necessary to communicate both internally and externally on the network will need to be installed. | 2018-11-07 | 2018-12-12 | 134 | 26 | 1 | 2018-11-07 | 2018-11-12 | Complete |  | 2018-12-17 | Joe Shmoe | Felicia Ainslie
3.1 | Install cabling | Install cat7 cabling throughout the facility. | 2018-11-07 | 2018-11-28 | 80 | 12 |  | 2018-11-07 | 2018-11-12 | Complete | Network Engineer time off for personal reasons. | 2018-11-29 | Joe Shmoe | Felicia Ainslie
3.2 | Install all access points | Install access points and routers. | 2018-11-29 | 2018-12-03 | 8 | 2 | 3.1 | 2018-11-29 | 2018-11-30 | Complete | Delieveries delayed due to the holidays. | 2018-12-03 | Joe Shmoe | Felicia Ainslie
3.3 | Install modem(s) | Install modem(s) to allow devices to connect to the internet. | 2018-12-03 | 2018-12-04 | 4 | 1 | 3.1 | 2018-12-03 | 2018-11-30 | Complete | Delieveries delayed due to the holidays. | 2018-12-03 | Joe Shmoe | Felicia Ainslie
3.4 | Install switches | Install switches to allow all devices to connect to the network. | 2018-12-05 | 2018-12-07 | 4 | 1 | 3.1 | 2018-12-05 | 2018-12-04 | Complete | Delieveries delayed due to the holidays. | 2018-12-05 | Joe Shmoe | Felicia Ainslie
3.5 | Install servers | Install servers to provide high-availablity, storage, and failover. | 2018-12-05 | 2018-12-07 | 10 | 2 | 3.1 | 2018-12-05 | 2018-12-05 | Complete | Delieveries delayed due to the holidays. | 2018-12-06 | Joe Shmoe | Felicia Ainslie
3.6 | Connect devices to network | Connect the devices to ethernet cabling, access points, switches, routers, modems, and servers. | 2018-12-10 | 2018-12-12 | 10 | 2 | 3.1, 3.2, 3.3, 3.4, 3.5 | 2018-12-10 | 2018-12-07 | Complete |  | 2018-12-10 | Joe Shmoe | Felicia Ainslie
3.6.1 | Connect all access points | Connect access points and routers to the appropriate switches. | 2018-12-10 | 2018-12-12 | 2 |  | 3.1, 3.2, 3.4 | 2018-12-10 | 2018-12-10 | Complete |  | 2018-12-10 | Joe Shmoe | Felicia Ainslie
3.6.2 | Connect switches | Connect all switches to the appropriate modem(s). | 2018-12-10 | 2018-12-12 | 1 |  | 3.3, 3.6.1 | 2018-12-10 | 2018-12-11 | Complete |  | 2018-12-11 | Joe Shmoe | Felicia Ainslie
3.6.3 | Power on | Turn on the modems, routers, switches, and computers. | 2018-12-11 | 2018-12-12 | 1 |  | 3.6.1, 3.6.2 | 2018-12-11 | 2018-12-11 | Complete |  | 2018-12-11 | Joe Shmoe | Felicia Ainslie
3.7 | Configure network hardware | Configure the network to allow all devices to succesfully connect to the network. | 2018-12-12 | 2018-12-19 | 20 | 5 | 3.6 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-12 | Joe Shmoe | Felicia Ainslie
3.7.1 | Configure Routers | The routers need to be configured for accessability and security. | 2018-12-12 | 2018-12-19 | 8 | 1 | 3.6 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-12 | Joe Shmoe | Felicia Ainslie
3.7.1.1 | Access webui for all routers | Use the IP address of each router to configure the settings for it . | 2018-12-12 | 2018-12-14 | 2 |  | 3.6 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-12 | Joe Shmoe | Felicia Ainslie
3.7.1.1.1 | Change router usernames/passwords | Change all router usernames and passwords to a combination of letters, numbers, and symbols. Take note of these changes and document them somewhere safe. | 2018-12-12 | 2018-12-14 | 2 |  | 3.7.1.1 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-12 | Joe Shmoe | Felicia Ainslie
3.7.1.1.2 | Add WPA2 Security | Set encyption security measures using strong passphrases for wireless access. | 2018-12-12 | 2018-12-14 | 2 |  | 3.7.1.1 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-12 | Joe Shmoe | Felicia Ainslie
3.7.1.1.3 | Change SSID | Choose a descriptive name for the network so staff members can easily identify it. | 2018-12-12 | 2018-12-14 | 1 |  | 3.7.1.1 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-13 | Joe Shmoe | Felicia Ainslie
3.7.1.1.4 | Change Network Channel | Switch routers to use channel 11 for minimal interference. | 2018-12-12 | 2018-12-14 | 1 |  | 3.7.1.1 | 2018-12-12 | 2018-12-12 | Complete |  | 2018-12-13 | Joe Shmoe | Felicia Ainslie
3.7.2 | Configure Switches | Switches need to be configured to maximize the networks broadcast and keep it secure. | 2018-12-17 | 2018-12-19 | 12 | 2 | 3.6.2 | 2018-12-17 | 2018-12-13 | Complete |  | 2018-12-17 | Joe Shmoe | Felicia Ainslie
3.7.2.1 | VLANs | Divide the network into separate virtual local area networks for each department. | 2018-12-17 | 2018-12-19 | 4 | 1 | 3.6.2 | 2018-12-17 | 2018-12-13 | Complete |  | 2018-12-14 | Joe Shmoe | Felicia Ainslie
3.7.2.2 | RSTP | Provide redundancy by configuring the Rapid Spanning Tree Protocol and dedicate one switch as the Root. | 2018-12-17 | 2018-12-19 | 4 | 1 | 3.6.2 | 2018-12-17 | 2018-12-15 | Complete |  | 2018-12-17 | Joe Shmoe | Felicia Ainslie
3.7.2.3 | Port Security | Ensure the appropriate device Mac Addresses are assigned to definte ports. | 2018-12-17 | 2018-12-19 | 4 | 1 | 3.6 | 2018-12-17 | 2018-12-15 | Complete |  | 2018-12-17 | Joe Shmoe | Felicia Ainslie
4 | Extra Security Measures |  | 2018-11-16 | 2018-12-14 | 10 | 2 | 1.1, 1.2, 1.2.1, 1.2.2, 1.2.3, 3.5 | 2018-11-16 | 2018-11-16 | Complete |  | 2018-12-11 | Lisa Frank | Felicia Ainslie
4.1 | Add Welcome Security Message | Add a message that appears during device powering on to inform users of legal actions that may be taken if property is misused. | 2018-11-16 | 2018-11-22 | 4 | 1 | 1.1, 1.2, 1.2.1, 1.2.2, 1.2.3 | 2018-11-16 | 2018-11-12 | Complete |  | 2018-11-16 | Lisa Frank | Felicia Ainslie
4.2 | Add Physical Locks | Add physical locks to desktop towers and servers. | 2018-12-08 | 2018-12-14 | 6 | 1 | 1.2, 3.5 | 2018-12-08 | 2018-12-10 | Complete |  | 2018-12-11 | Lisa Frank | Felicia Ainslie
5 | Adjust First Floor Design | Ensure first floor can walk between north and south wings uninterupted. | 2018-12-26 | 2018-12-31 | 12 | 2 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.6 | 2018-12-24 | 2018-12-24 | Complete | Change Request Form Effective 12/20/2018 | 2018-12-26 | Joe Shmoe | Felicia Ainslie
5.1 | Access Points | Place access point to allow for continual connectivity through the hall between the north and south wings of the facility. | 2018-12-26 | 2018-12-31 | 12 | 2 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.6 | 2018-12-24 | 2018-12-24 | Complete | Change Request Form Effective 12/20/2019 | 2018-12-26 | Joe Shmoe | Felicia Ainslie
6 | Test | Thorough testing needs to be completed to ensure devices, software, and network equipment are functioning appropriately. | 2018-12-20 | 2018-12-26 | 80 | 5 | 1, 2, 3, 4 | 2018-12-20 | 2018-12-18 | Complete |  | 2019-01-04 | Les Dooit | Felicia Ainslie
6.1 | Ensure network functionality | Devices need to be successfully connected to the network. | 2018-12-20 | 2018-12-23 | 15 | 3 | 3.7 | 2018-12-20 | 2018-12-18 | Complete |  | 2018-12-27 | Les Dooit | Felicia Ainslie
6.1.1 | Ensure network functionality in first floor hall | Test that devices can connect between the north and south wings of the first floor. (Change Request Form effective 12/20/2018). | 2018-12-31 | 2018-01-04 | 5 | 1 | 3.7, 5 | 2018-12-31 | 2018-12-27 | Complete | Change Request Form Effective 12/20/2019 | 2018-12-27 | Les Dooit | Felicia Ainslie
6.1.2 | Ensure network funcionality on second floor | Test that devices can connect to the network on the second floor and access their tools/ internet. | 2018-12-31 | 2018-01-04 | 5 | 1 | 3.7 | 2018-12-31 | 2018-12-18 | Complete |  | 2018-12-18 | Les Dooit | Felicia Ainslie
6.1.3 | Ensure network funcionality on third floor | Test that devices can connect to the network on the third floor and access their tools/ internet. | 2018-12-31 | 2018-01-04 | 5 | 1 | 3.7 | 2018-12-31 | 2018-12-19 | Complete |  | 2018-12-19 | Les Dooit | Felicia Ainslie
6.2 | Test network speeds | Devices need to connect quickly to the network and run quickly using the network. | 2018-12-20 | 2018-12-27 | 15 | 3 | 3.7 | 2018-12-20 | 2018-12-20 | Complete |  | 2019-01-02 | Les Dooit | Felicia Ainslie
6.2.1 | Ensure network speeds in first floor hall | Test that devices have adequate network speed between the north and south wings of the first floor. (Change Request Form effective 12/20/2018). | 2019-01-02 | 2019-01-04 | 5 | 1 | 3.7, 5 | 2018-12-30 | 2018-12-30 | Complete | Change Request Form Effective 12/20/2019 | 2019-01-02 | Les Dooit | Felicia Ainslie
6.2.2 | Ensure network speeds on the second floor | Test that devices have adequate network speeds. | 2018-12-30 | 2019-01-04 | 5 | 1 | 3.7 | 2018-12-23 | 2019-12-20 | Complete |  | 2018-12-20 | Les Dooit | Felicia Ainslie
6.2.3 | Ensure network speeds on the third floor | Test that devices have adequate network speeds. | 2018-12-30 | 2019-01-04 | 5 | 1 | 3.7 | 2018-12-26 | 2018-12-23 | Complete |  | 2018-12-23 | Les Dooit | Felicia Ainslie
6.3 | Test network coverage | Devices need to be able to connect from anywhere on the top two floors and from the north or south wings on the first floor. | 2018-12-30 | 2019-01-07 | 15 | 3 | 3.7 | 2018-12-30 | 2018-12-23 | Complete | Delays due do Network coverage issues. | 2019-01-03 | Les Dooit | Felicia Ainslie
6.3.1 | Ensure network coverage in first floor hall | Test that network covers a straight path to/from the north and south wings of the first floor. (Change Request Form effective 12/20/2018). | 2019-01-03 | 2019-01-07 | 5 | 1 | 3.7, 5 | 2019-01-03 | 2019-01-03 | Complete | Change Request Form Effective 12/20/2019 | 2019-01-03 | Les Dooit | Felicia Ainslie
6.3.2 | Ensure network coverage on second floor | Test that the network covers 100% of the second floor. | 2018-12-30 | 2019-01-07 | 5 | 1 | 3.7 | 2018-12-30 | 2018-12-23 | Complete |  | 2018-12-23 | Les Dooit | Felicia Ainslie
6.3.3 | Ensure network coverage on third floor | Test that the network covers 100% of the third floor. | 2018-12-30 | 2019-01-07 | 5 | 1 | 3.7 | 2018-12-30 | 2018-12-23 | Complete |  | 2018-12-26 | Les Dooit | Felicia Ainslie
6.4 | Test Security Measures | Ensure security measures prevent harm to devices and data. | 2019-01-07 | 2019-01-11 | 40 | 5 | 3.7, 3.7.2.3 4, 4.1, 4.2 | 2019-01-07 | 2018-12-26 | Complete | Delays due to past issues and absenteeism. |  | Les Dooit | Felicia Ainslie
6.4.1 | Test physical locks | Ensure physical locks are functional. | 2019-01-07 | 2019-01-11 | 2 |  | 4.2 | 2019-01-07 | 2018-12-26 | Complete |  | 2018-12-26 | Les Dooit | Felicia Ainslie
6.4.1.1 | Test Device Locks | Ensure that physical locks on servers and computers are functional. | 2019-01-07 | 2019-01-11 | 1 |  | 4.2 | 2019-01-07 | 2018-12-26 | Complete |  | 2018-12-26 | Les Dooit | Felicia Ainslie
6.4.1.2 | Test Server door locks | Ensure that server door card access can not be accessed in other methods. | 2019-01-07 | 2019-01-11 | 1 |  | 4.2 | 2019-01-07 | 2018-12-26 | Complete |  | 2018-12-26 | Les Dooit | Felicia Ainslie
6.4.2 | Test Port security | Ensure that ports are properly assigned and plugging other devices into them does not allow connectivity. | 2019-01-07 | 2019-01-11 | 8 | 1 | 3.7.2.3 | 2018-12-26 | 2018-12-26 | Complete |  | 2018-12-27 | Les Dooit | Felicia Ainslie
6.4.3 | Pen Testing | Ensure that the network and devices on it cannot be hacked. | 2019-01-07 | 2019-01-11 | 11 | 2 | 3.7 | 2018-12-27 | 2018-12-27 | Complete |  | 2018-12-31 | Les Dooit | Felicia Ainslie
6.4.4 | Stress Testing | Ensure that the network can handle the amount of stress anticipated and that the failover's in place function appropriately. | 2019-01-07 | 2019-01-11 | 11 | 2 | 3.7 | 2018-12-31 | 2019-01-02 | Complete |  | 2019-01-04 | Les Dooit | Felicia Ainslie
7 | Launch | The project needs to be finalized and the network fully available to all employees at the new Future Tech Inc. location. | 2019-01-12 | 2019-01-20 | 10 | 2 | 1, 2, 3, 4, 5, 6, 7 | 2019-01-12 | 2019-01-07 | Complete |  | 2019-01-08 | Felicia Ainslie | Felicia Ainslie
7.1 | Have all employees connect to the network | The employees should check that their devices automatically connect to the network without them typing in the password. | 2019-01-12 | 2019-01-15 | 5 | 1 | 1, 2, 3, 4, 5, 6, 7 | 2019-01-12 | 2019-01-07 | Complete |  | 2019-01-07 | Felicia Ainslie | Felicia Ainslie
7.1.1 | Have employees begin work as normal | Employees should resume normal production using the newly developed network. | 2019-01-15 | 2019-01-16 | 1 |  | 1, 2, 3, 4, 5, 6, 7 | 2019-01-15 | 2019-01-07 | Complete |  | 2019-01-07 | Felicia Ainslie | Felicia Ainslie
7.2 | Product Completion Review | Email all stakeholders a summary of the successful deliverables and outstanding items. | 2019-01-16 | 2019-01-18 | 4 | 1 | 1, 2, 3, 4, 5, 6, 7 | 2019-01-16 | 2019-01-08 | Complete |  | 2019-01-08 | Felicia Ainslie | Felicia Ainslie
7.3 | Final Status Report | Submit the final status report to stakeholders. | 2019-01-16 | 2019-01-18 | 1 |  | 1, 2, 3, 4, 5, 6, 7 | 2019-01-16 | 2019-01-08 | Complete |  | 2019-01-08 | Felicia Ainslie | Felicia Ainslie
7.4 | Lessons Learned | Document all lessons learned for the project. | 2019-01-17 | 2019-01-20 | 1 |  | 1, 2, 3, 4, 5, 6, 7 | 2019-01-17 | 2019-01-08 | Complete |  | 2019-01-08 | Felicia Ainslie | Felicia Ainslie
Formulas:
Planned Start Date = [Must Start by Date]