## Sheet1
Project name: | Tech Network | Project number: | 243 |  | Project Manager’s name: | Felicia Ainslie
Type of risk | Describe the impact or characteristics | Examined | Estimated likelihood % | Risk description | Mitigation strategy | Resource
Project schedule | Increased project time | q | 50% | Delays in the project due to various events. This may be due to team member, vendor, or natural causes. | * Assign a secondary "backup" team member to tasks to ensure they are completed should the main team member become unavailble. * Agenda Director tracks project progress and reports any potential scheduling threats immediately. * Create more than one project schedule that involves increasing labor hours per day to limit going beyond launch date. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Budgets/funding | Increased cost | q | 50% | Additional hardware or labor is necessary to complete tasks. Initial costs were underestimated. | * Contact vendor directly and expedite additional hardware requirements. * Assign available team members to assist with new labor requirements. | Lukas, J. A. (2002). It works! Risk management on an IS project. Retrieved from https://www.pmi.org/learning/library/risk-management-information-systems-project-111
Personnel issues | Loss of key team member; not enough team members assigned to project | q | 40% | Resource competion may result in team members being re-assigned to new projects. Team members may also be unavailable due to personal issues. | * Develop a secondary schedule that involves team members taking over additional roles. * Ensure chosen team members can fill additional roles if necessary or have staff that is willing to train for this. | Lukas, J. A. (2002). It works! Risk management on an IS project. Retrieved from https://www.pmi.org/learning/library/risk-management-information-systems-project-111
Quality | Does not meet standards | q | 20% | Network speeds are under the 30 Mbps download and/or 10 Mbps upload speeds required. | * Add more access points. * Check with ISP to see if faster speeds are available. * Look into switching ISP. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Key stakeholder consensus | Conflicts and project delays | q | 5% | Stakeholders disagree on the required network coverage for each floor. | * Educate stakeholders on the type of work that will be done on each floor. * Educate stakeholders on the cost of increasing network speeds or increasing coverage. * Educate stakeholders on the speed needs for a single user on each floor. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Scope changes | Increased project time and costs | q | 20% | Stakeholders determined additional requirements were necessary to make project launch successful. | * Add time onto estimated current schedule to account for potential changes such as additional hardware installation. | Lukas, J. A. (2002). It works! Risk management on an IS project. Retrieved from https://www.pmi.org/learning/library/risk-management-information-systems-project-111
Project plans | Increased project time and costs, impact on quality, and poor direction and communication | q | 30% | Success criteria did not include all key details. Some subtasks may have not been defined. | * Hold stakeholder meeting to ensure all details of the project are fully developed prior to starting the project. * Hold follow up meetings prior to each deliverables completion to ensure no further action is required. * Document all meetings held. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Project management methodology | Increased project time and costs | q | 3% | Team members are not fully trained/informed of their expectations prior to task completion. | * Hold team member meeting's weekly to ensure staff is informed about their expectations. * Document all team meetings held. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Security risk | Network vulnerable to attacks | q | 0.35% | Computers not being equipped with proper anti-virus/anti-malware/ firewall rules. | *Post installation have each employee run a scan using the software. If they state they cannot find it, ensure it is installed. * Complete penetration testing on all devices. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Vendor issues | Delivery delays | q | 35% | Miscommunications regarding vendor expectations. | * Ensure contract contains expected delivery dates. * Have adequate contact with secondary vendors to fill in should the elected fail to meet their obligations. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Contract risks | Project delays; increased costs | q | 10%-40% | Vendors not following contractual agreements and/or being unreliable when attempting to contact. | * Ensure contracts have all constraints and requirements detailed. * Have adequate contact with secondary vendors to fill in should the elected fail to meet their obligations. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Weather or natural disasters | Schedule delays, delivery delays, and increased costs | q | 50%-70% | Snow or weather conditions may affect hardware delivery. | * Complete contracts and schedule deliveries to arrive prior to when there are scheduled to be installed. * Assign team members to different roles/tasks to complete while waiting for delivery of hardware. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Technology risks | Not available when needed | q | 15% | Purchased hardware is defective. | * Continue completing tasks while working around the defective device. * Inform vendor immedialtely upon discover to issue a RMA. * Check available resources for a temporary replacement. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Project complexity | Inexperience of project team | q | 25% | The project team has not previously worked together to create a network of this size. | * Provide educational resources to all team members. * Educate team members on how the project will go. * Inform team members to stay task oriented to avoid getting overwhelmed by the size of the project. * Create team building exercises to build trust among team members. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Project manager skills | Inexperience of project manager | q | 50% | This is the project manager's first network project. | * Work closely with the network engineer to understand their needs. * Include a resource plan that provides details on what tasks will be accomplished and how they are done. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/
Team skills and abilities | Inexperience of team members; lack of training | q | 35% | Team members are not fully trained/informed of their expectations. Educated team members may not have hands on experience. | * Include a resource plan that provides details on what tasks will be accomplished and how they are done. * Encourge team members to voice their opinions and ask questions regarding the tasks required of them. * Perform background checks and detailed interviews. * Offer additional training and materials prior to being asked for them if possible. | My Spreadsheet Templates. (2018, July 29). Risk Matrix Template Excel Unique Great Risk Ysis Matrix Template Risk Assessment Matrix. Retrieved from http://divaandmeproductionsinc.com/risk-matrix-template-excel/risk-matrix-template-excel-unique-great-risk-ysis-matrix-template-risk-assessment-matrix/