## Resources
Task Name | Duration | Start | Finish | Predecessors | Resource Names | Milestone | Cost | % Work Complete
Analysis | 4 days | Wed 2/3/21 | Mon 2/8/21 | 4 | Ms. Ainslie | No | 1760 | 100%
Analyze Hardware | 2 days | Wed 2/3/21 | Thu 2/4/21 |  | Mr. Lyst | No | 560 | 100%
Analyze Software | 2 days | Fri 2/5/21 | Mon 2/8/21 |  | Mr. Lyst | No | 560 | 100%
AUP | 5 days | Tue 2/9/21 | Mon 2/15/21 | 7 |  | Yes | 800 | 100%
Create Contracts | 2 days | Tue 2/9/21 | Wed 2/10/21 |  | Ms. Ainslie | No | 320 | 100%
Contracts Signed | 3 days | Thu 2/11/21 | Mon 2/15/21 |  | Ms. Ainslie | No | 480 | 100%
Prepare Hardware | 14 days | Tue 2/16/21 | Fri 3/5/21 | 10 | Web Cams[200],Ms. Ainslie | No | 15792 | 100%
Update Computers | 7 days | Tue 2/16/21 | Wed 2/24/21 |  | Mr. Fixit | No | 896 | 100%
Install web cams | 7 days | Thu 2/25/21 | Fri 3/5/21 |  | Mr. Fixit | No | 896 | 100%
Prepare Software | 6 days | Tue 2/16/21 | Tue 2/23/21 | 13 | MDM[200],VPN[200],Ms. Ainslie | No | 21672 | 100%
Install MDM | 6 days | Tue 2/16/21 | Tue 2/23/21 |  | Mr. Micro | No | 2016 | 100%
Install VPN | 6 days | Tue 2/16/21 | Tue 2/23/21 |  | Mr. Micro | No | 2016 | 100%
Prepare Network | 14 days | Tue 2/16/21 | Fri 3/5/21 |  | Hotspots[20],Routers[43],Ms. Ainslie | No | 15829 | 100%
Network Check | 5 days | Tue 2/16/21 | Mon 2/22/21 |  | Mrs. Wan | No | 1640 | 100%
Bandwidth | 5 days | Tue 2/16/21 | Mon 2/22/21 |  |  | No | 0 | 100%
Latency | 5 days | Tue 2/16/21 | Mon 2/22/21 |  |  | No | 0 | 100%
Packet loss | 5 days | Tue 2/16/21 | Mon 2/22/21 |  |  | No | 0 | 100%
Configuration | 5 days | Tue 2/23/21 | Mon 3/1/21 | 14 | Mrs. Wan,Cat6[60] | No | 6482 | 100%
Enable Multicast | 5 days | Tue 2/23/21 | Mon 3/1/21 |  |  | No | 0 | 100%
Confirm No Double Nat | 5 days | Tue 2/23/21 | Mon 3/1/21 |  |  | No | 0 | 100%
Firewall Rules | 5 days | Tue 2/23/21 | Mon 3/1/21 |  |  | No | 0 | 100%
Disable SIP ALG | 5 days | Tue 2/23/21 | Mon 3/1/21 |  |  | No | 0 | 100%
Install New Routers | 9 days | Tue 2/23/21 | Fri 3/5/21 |  | Mrs. Wan | No | 2952 | 100%
Setup Routers | 7 days | Tue 2/23/21 | Wed 3/3/21 |  |  | No | 0 | 100%
Setup Hotspots | 2 days | Thu 3/4/21 | Fri 3/5/21 |  |  | No | 0 | 100%
Testing | 14 days | Tue 2/23/21 | Fri 3/12/21 |  | Ms. Ainslie | Yes | 6800 | 100%
Test MDM | 2 days | Tue 2/23/21 | Wed 2/24/21 | 11 |  | No | 1152 | 100%
Test Alerts | 2 days | Tue 2/23/21 | Wed 2/24/21 |  | Ms. Perfect | No | 576 | 100%
Test compromising MDM | 2 days | Tue 2/23/21 | Wed 2/24/21 |  | Ms. Perfect | No | 576 | 100%
Test VPN | 2 days | Tue 3/2/21 | Wed 3/3/21 | 12 |  | No | 1728 | 100%
Resource Accessibility | 2 days | Tue 3/2/21 | Wed 3/3/21 |  | Ms. Perfect | No | 576 | 100%
Connectivity | 2 days | Tue 3/2/21 | Wed 3/3/21 |  | Ms. Perfect | No | 576 | 100%
Test Access Controls | 2 days | Tue 3/2/21 | Wed 3/3/21 |  | Ms. Perfect | No | 576 | 100%
Test Webcams | 2 days | Mon 3/8/21 | Tue 3/9/21 | 9 | Mr. Lyst | No | 560 | 100%
Test Connectivity | 4 days | Tue 3/9/21 | Fri 3/12/21 | 33 | Mr. Lyst | No | 1120 | 100%
Test Hotspots | 2 days | Tue 3/9/21 | Wed 3/10/21 |  |  | No | 0 | 100%
Test Routers | 2 days | Thu 3/11/21 | Fri 3/12/21 |  |  | No | 0 | 100%
Assessments | 4 days | Mon 3/15/21 | Thu 3/18/21 | 26 |  | No | 1120 | 100%
QA Review | 1 day | Mon 3/15/21 | Mon 3/15/21 |  | Ms. Ainslie | No | 160 | 100%
Stakeholder Notice | 1 day | Tue 3/16/21 | Tue 3/16/21 |  | Ms. Ainslie | No | 320 | 100%
Final Status | 1 day | Wed 3/17/21 | Wed 3/17/21 | 40 | Ms. Ainslie | No | 320 | 100%
Lessons Learned | 1 day | Thu 3/18/21 | Thu 3/18/21 | 41 | Ms. Ainslie | No | 320 | 100%