## Slide 1: Remote Staff Initiative
By Felicia Ainslie
Purdue University Global

## Slide 2: Project Overview
Remote work
Security from anywhere
Reduce carbon footprint
Remain competitive
Notes: VoIP Fan offers voice over internet protocol communication services for thousands of customers and is the home to just over one thousand employees. The organization has made a discovery that the number of organizations allowing staff members to work from home is increasing, so a survey was sent out by human resources to assess employee interest in remote work.. After high interest in the idea of remote work VoIP Fan elected to initiate a project that would allow employees to work from home thus allowing staff to spend more time with their families. The setup was to allow secure access to company resources from any location thus allowing the organization to also reduce their carbon footprint while becoming a more competitive employer. This presentation will explore the details learned from this project to assist with the assessment of future projects which may be similar in nature.

## Slide 3: Stakeholder Expectations
Project manager
Systems analyst
Quality assurance specialist
Software engineer
Network engineer
Hardware technician
Notes: The project manager role was filled by myself and included a variety of obligations. Examples of these tasks include developing and managing the project's budget , schedule, communication plan, and risk mitigation. Documentation was also created throughout the project to note any changes in addition to milestone successes or failures. In the role of a project manager, it was also critical to ensure quality was maintained throughout the project and that actions remained aligned with the initial scope.
The system analyst role initially involved analyzing the existing network topology , security measures, software, hardware, and resource access. These matters were evaluated to determine if adequate solutions existed to allow employees to work from home without additional tools, and if not research potential solutions. Employee documentation was also developed to assist with the initial setup for remote staff. They role would also involve training remote staff during the transition. Within the testing phases this role evolved to include testing webcams, routers, and hotspots to ensure functionality and quality criteria were upheld.
The quality assurance specialist was responsible for testing all software, hardware, and network components. Prior to the commencement of testing documentation was created to ensure all points were met before the project could continue or be deemed a success. It was critical that alerts and access controls be tested for security purposes and for functionality as well. Additional factors that were tested for included ease of use and accessibility.
The software engineer utilized the research from the system analyst to find the appropriate software that would allow staff to remotely access company resources in a secure environment. Once the products were chosen, the software engineer worked side by side with the project manager to procure the software from the vendor. The software would then be installed on all remote devices and basic functionality confirmed after install.
The network engineer worked primarily with the remote staff and their internet service providers to ensure their network and equipment could maintain a reliable connection. In addition to this it was important to confirm the equipment was properly configured for a VoIP environment. In the event changes were required documentation would be made to note the specifics of what was changed for what employee. For a subset of employees this involved purchasing and installing new routers and or hot spots to allow proper configuration and quality connection.
The hardware technician was responsible for assessing all remote staff computers to confirm they were in adequate condition or better for either office or remote work. This consisted of updating operating systems and drivers as needed. Webcams were also installed by the hardware technician and configured as necessary to ensure basic functionality was achieved.

## Slide 4: Milestones
Analysis
Acceptable Use Policy
Prepare Hardware
Prepare Software
Prepare Network
Testing
Assessments
Notes: The remote staff initiative consisted of seven milestones. The first of these seven was analysis which consisted of analyzing existing systems to determine what may or may not need to be replaced. Following this was the development and signing of the acceptable use policy. Developing the acceptable use policy was a critical component for this project to ensure that all staff members understood what was expected with working remotely. Hardware preparation involved installing the webcams and confirming the computers were up to date and functioning properly. Software preparation consisted of installing the mobile device management and virtual private network software that would allow staff to securely access resources outside the company network. Preparing the network involved confirming there was adequate bandwidth, there was no latency, settings that were not compatible with VoIP were altered, and both routers and hot spots were installed . The testing phase checked all the previously mentioned actions to confirm that the remote staff would be able to securely and easily access the appropriate resources with little to no issue. Finally, the assessments phase involved reviewing the quality of the aforementioned actions, providing notice to the stakeholders of the project's conclusion and results, outlining the final status of the project, and documenting the lessons learned throughout the project.

## Slide 5: Deliverables
AUP contracts signed
Install webcams
Install MDM
Install VPN
Install Routers
Notes: This project included five deliverables, the first of which was having the acceptable use policy contract signed by employees who wish to work remotely. The second deliverable was the installation of the webcams. This was critical as the webcams were to be used for one on one meetings or team meetings, depending on the employers need. The third deliverable was to install the mobile device management software. The MDM software would allow VoIP fan to know what the employee was doing as they were doing it and would also allow them to remotely wipe or review resources that may have been inappropriately accessed. The fourth deliverable was the installation of the virtual private network. This software would allow remote employees to access company resources as needed. Finally, the routers and hotspots were the last deliverable. While not all employees required this it was critical for the subset that did have them installed to ensure the equipment could be properly configured with minimal to no latency or packet loss.

## Slide 6: Schedule
Start 2/3/21
Finish 3/18/21
Milestones
Feb 9
Feb 16
Feb 23
Mar 2
Mar 9
Mar 16
✔Analysis 2/8/21
✔Assessments 3/18/21
✔Prep Hardware 3/5/21
✔Prep Software 2/23/21
✔Prep Network 3/5/21
✔AUP 2/15/21
✔Testing 3/12/21
Start 2/3/21
Finish 3/18/21
Deliverables
Feb 9,
Feb 16
Feb 23
Mar 2
Mar 9
Mar 16
✔Install VPN 2/16/21 - 2/23/21
✔Install
Web cams 2/25/21 - 3/5/21
✔
Contracts Signed 2/11/21 -2/15/21
✔Install MDM 2/16/21 - 2/23/21
✔Install New Routers 2/23/21 - 3/5/21
Notes: The graph shown before you demonstrates the schedule based on milestones and deliverables. Within the first graph you will see the completion dates of each milestone described in previous slides. Below this you will see the start and completion date of each milestone. When compared to the data from the work breakdown structure, there were no differences in start or completion dates despite having some challenges. These challenges included delays on the procurement of software, issues with packet loss by a subset of staff members, and the loss of a team member within the testing phase

## Slide 7: Material Expenses
Cost | Material | Units
$14,000.00 | Web Cams | 200
$8,040.00 | VPN | 200
$9,600.00 | MDM | 200
$6,407.00 | Routers | 43
$1,995.00 | Cat6 | 60
$1,300.00 | Hotspots | 20
Notes: The chart before you displays the material expenses that were accumulated throughout the project. A consistent number of units was purchased for the webcams, VPN, and MDM software as there were 200 remote staff members. The Logitech C920S HD Pro webcams were chosen as the camera offer high quality at a low price and even include a lens cover to offer privacy to remote staff members (Cunningham & Pinola, 2020). Perimeter 81 was the VPN of choice due to the many features such as policy-based segmentation, reporting, two-factor authentication, SSO, site-to-site interconnectivity, and 24/7 support (Perimeter 81, n.d.). For the MDM Scalefusion was an easy choice to make based on the large number of five-star reviews, location tracking, remote control, reporting, and multi-operating system support (G2.com, Inc, n.d.). For the forty-three staff members that required replacement network equipment, Cisco’s RV100 series routers were chosen. These routers were selected since the organization already utilizes Cisco products in office and they are capable of maintaining the required criteria for up to fifty users which will be more than enough for their intended use both for work and personal use (Cisco, n.d.). Cat6 twisted shielded ethernet cables were purchased in bulk with lifetime warranties to ensure all remote staff was able to connect directly to their routers (Cables.com, n.d.). Finally, hotspots were purchased to confirm a subset of remote staff with poor internet connectivity would remain operational during ISP outages. The ZTE Max Connect hotspot was chosen as it offers high data transfer rates, WPA2 for security, and can be managed online all for a low price (Amazon, n.d.).

## Slide 8: Labor Expenses
Cost | Name | Work
$2,800.00 | Systems Analyst | 80 hrs
$6,232.00 | Network Engineer | 152 hrs
$4,032.00 | Software Engineers | 96 hrs
$2,880.00 | Quality Assurance | 80 hrs
$4,320.00 | Project Manager | 216 hrs
$1,792.00 | Hardware Technician | 112 hrs
Notes: The expenses within this chart depict the number of hours worked by each stakeholder in addition to the total amount each team member was paid for their work within the project. Salaries for these individuals were based on the median wages of similar roles taken from ZipRecruiter (n.d.). Not all milestones were of the same length, so the hours worked vary and they were based on a Monday through Friday schedule. Additional details regarding the salaries may be provided after this meeting upon request.

## Slide 9: Budget Variance
Budget
Initial Estimate
Final Cost
Notes: VoIP Fan set a budget of $250,000 aside for the remote staff initiative. This proved to be far more than the project would require as the initial estimate with labor and material costs totaled only $71,934. After calculating the final material and labor costs the total cost at the conclusion of the project was $63,773. Changes that reduced the initial estimate included a reduction in number of required routers and a change of personnel.

## Slide 10: Success Factors
Risk Management
Communication
Quality
Notes: Together the project team was able to succeed in a variety of ways which included mitigating risks, communicating regularly, and working to the best of their ability to ensure quality. The risk management plan was a large part of how the team was able to work around and predict potential issues. With that said it was only during the network checks of remote staff members that the trend in packet loss led to the discovery of a common backbone Internet service provider. This quick identification allowed staff to predict that employees that live in the surrounding area will likely experience the same events and require hot spots like the initial remote staff did. This prediction will assist with future projects should other departments go remote. The project team was also very responsive to communication made by team members to assist with developing a plan for the loss of the quality assurance specialist team member. It was through this communication that it was decided the system analyst would fulfill the role. Finally, the initial quality assurance documentation that was created by the specialist was a critical component to the success of this project. This documentation allowed us to ensure that all quality criteria initially requested in the project proposal was met or exceeded in the final product.

## Slide 11: Risk Mitigation
Internet Issues
Unsupported network equipment
Inappropriate access
Delays
Notes: Risk mitigation plans were developed with the assistance of the network engineer, the software engineer, and the system analyst. The anticipated issues for the remote staff initiative included four likely events. The first three events involve the remote staff networks. Internet issues such as outages, inadequate bandwidth , latency, or packet loss are all potential issues for any internet connection. For home users the chances of these occurring are much higher as there is no backup connection. To mitigate this risk net checks we're done and any connection that was deemed unreliable was remedied with the purchase of a hot spot to act as that backup connection.
Another potential issue would occur if the existing equipment did not support VoIP or could not be configured to support VoIP. The network engineer was able to avoid this issue by collecting information from the remote users on their internet service providers ahead of time, contacting the ISPs for a list of supported devices, and then cross referencing the lists to discover what router would be compatible for all remote users.
The third risk mitigated by our network engineer was delays in configuring staff networks. Prior to communicating with staff members about scheduling the network configuration changes and connectivity tests the network engineer developed a checklist for remote staff to use. This list described what settings needed to be checked in addition to what information would be asked such as passwords, makes and models of equipment, internet service provider name, and the speeds that were being paid for. This checklist was then provided to all remote staff members and they were required to schedule their network checks within a specific period of time, or they would be unable to work remotely. The acceptable use policy also outlined these requirements to avoid potential issues with staff members refusing network access for failing to provide it in a timely manner.
The final anticipated risk involved resource accessibility. The concern with this was that remote staff member would either have too much or too little access to company resources. To mitigate this risk the software engineer worked directly with these support staff managers to understand what requirements each support role had to perform their daily operational tasks. A list of unique circumstances was developed to expedite approval should these requirements change and any staff with varying permission requirements were addressed separately.

## Slide 12: Communication Plan
Kick-off meeting
Status reports
Milestone review
QA review
Lessons Learned
Notes: Aside from the quality assurance reviews, all meetings were to include all stakeholders to ensure open visibility to all status updates , changes, or issues. This project started with a kickoff meeting to discuss the scope of the project, budget , schedule, roles, and expectations. Status reports would be sent from each stakeholder to all stakeholders via email on a weekly basis. This open communication allowed the team to collaborate and manage their time properly. Milestone reviews were done through virtual meetings on Zoom and essentially involved discussing what was done and briefly discussing the testing phase for that milestone, if applicable. Quality assurance reviews were completed over the phone on a one-on-one basis. The final meeting was at the conclusion of the project to discuss the lessons learned so that documentation could be made to assist projects in the future.

## Slide 13: Quality Management
Hardware
Software
Network
Notes: Quality management was made possible through preparation and documentation for the hardware, software, and networking components of the project. Acceptance criteria for the hardware included having all computers up to date and webcams installed. For software, all computers were required to have MDM and VPN software installed to allow remote staff access to company resources in a secure manner. This required the software engineer to also verify that the software could not be disabled or compromised by the remote staff member in any way. Finally, the network preparation involved confirming that all networks had at least 10 megabytes up and down for bandwidth, latency was not to exceed 150 milliseconds, there was to be no packet loss, SIP ALG must be disabled, multicast must be enabled, firewall rules must allow connection to the organization, and only one device could perform network address translation on the network.

## Slide 14: Lessons Learned
Common ISP
Backup or cross trained staff
Notes: This project taught our team two major lessons that will aid in future projects for when additional departments begin working remotely or simply with other projects in general. The first major lesson was to pay attention to detail during assessments as it can assist with identifying trends. For the remote staff initiative, the trend identified was a common internet service provider that was causing packet loss for remote staff members. While our team was able to mitigate this risk, it is important to keep a watchful eye for common denominators to expedite a resolution. The second lesson learned was to always have a contingency plan for staff members. It does not matter the length of a project as circumstances can change at the drop of a hat. It is for this reason that it is important that all projects should have defined backup staff members or ensure that the staff members assigned to a project are cross trained and willing to take over any role for any staff member at any time.

## Slide 15: Best Practices
Communication
Preparation
Documentation
Notes: Best practices demonstrated through this project involved regular communication, ample preparation, and substantial documentation. These concepts are critical to the success of any project. Stakeholders should be properly educated on their expected deliverables, quality criteria, constraints, risks, and any other factors relevant to the project. With regular communication the team will be able to properly prepare for the upcoming project. Preparation will assist with limiting changes, reducing risks, expediting tasks, and remaining within the project’s scope. The communication and preparation techniques used for one project can be used to help others as well if properly documented which leads to the third best practice, documentation. Documenting changes, issues, research discoveries, or anything that has been accomplished can all benefit future projects. It is important to realize that just because a project is unique does not mean that the knowledge gained from the project is not valuable

## Slide 16: Ethical Issues
Dishonesty
Lack of effort
Poor Quality
Privacy
Monitoring
Notes: Despite the many benefits of the remote staff initiative there are a few ethical issues that are worth mentioning. One concern many have with remote work is privacy. While this may not seem to be an obvious issue as the staff member will be out of sight, it is important to consider the methods of how staff will be managed. Factors that must be considered include how will webcams be used. More specifically, will they be used to monitor staff? If so, it is important that this be documented with proof that the staff acknowledges and approves. Monitoring software is another cause for concern when it comes to privacy as employers must ensure that staff members understand that company property should not be used for personal use or it may be subject to data collection of private information (Smith, 2021).
Another ethical concern with remote work could be that employees feel less obligated to produce the same quality results they would in office. Overtime these remote staff members may begin to cut corners or avoid reporting incidents as they may feel like they will not be caught since no one can see them (Khan, 2020). This dishonesty can have a negative impact not only on the employee’s career if discovered, but also on the organization.

## Slide 17: Resources
Amazon. (n.d.). ZTE MAX Connect unlocked mobile WiFi hotspot 4G LTE GSM router MF928, up to 150mbps download speed, connect up to 10 devices, create a WLAN anywhere bundle with microfiber cloth. Retrieved from https://www.amazon.com/dp/B08F2WW1H1?tag=p00935-20&ascsubtag=03BHrE9ctFQmdLMpKKL59WR
Cables.com. (n.d.). 100Ft Cat6 shielded ethernet cable snagless blue. Retrieved from https://www.cables.com/100ft-cat6-shielded-ethernet-cable-snagless-blue.html?gclid=Cj0KCQiApsiBBhCKARIsAN8o_4gkOBbqBJq96qRcxMewlAypCRMAv9UQwrhlJrlFRRaTxr-__6ml3JQaAg4CEALw_wcB
Cisco. (n.d.). Small business Routers. Retrieved from https://www.cisco.com/c/en/us/solutions/small-business/networking/routers.html#~products
Cunningham, A. & Pinola, M. (2020). The best webcams. Retrieved from https://www.nytimes.com/wirecutter/reviews/the-best-webcams/
G2.com, Inc.. (n.d.). Scalefusion. Retrieved from https://www.g2.com/products/scalefusion/pricing
Khan, R. (2020). Work from anywhere trend intensifying ethics, and compliance issues. Retrieved from https://www.forbes.com/sites/roomykhan/2020/11/06/work-from-anywhere-trend-intensifying-ethics-and-compliance-issues/?sh=49ffe3882f38
Perimeter 81. (n.d.). Choose your perimeter 81 plan. Retrieved from https://www.perimeter81.com/pricing
Smith, E. (2021). Four ethical considerations for using employee monitoring software on remote workers. Retrieved from https://associationsnow.com/2021/03/four-ethical-considerations-for-using-employee-monitoring-software-on-remote-workers/
ZipRecruiter. (n.d.). Real salaries from real employers. Retrieved from https://www.ziprecruiter.com/Salaries